## Sheet1
Task | Effort | Scheduled | Completion
Come up with approach | 4h | 2015-04-13 | Completed
Verify approach | 4h | 2015-04-13 | Completed
Create to-do lijst | 2h | 2015-04-14 | Completed
Setup Git repo for the project | 2h | 2015-04-15 | Completed
Build RegEx filter | 6h | 2015-04-16 | Completed
Factorizing data and options sets | 8h | 2015-04-20 | Completed
Build HTML around the data sets | 8h | 2015-04-21 | Open
Display questions in sequence | 6h | 2015-04-22 | Open
CSS style | 2h | 2015-04-22 | Open
Clean up code and finalizing | 4h | 2015-04-23 | Open